## Slide 1
Project Fails due to Inadequate WBS
The solid foundation every stakeholder must know
PMI – Adelaide Chapter

## Slide 2
Basic WBS
Mechanics of WBS
WBS Association
Definition
Level Categories
Backward Pass Approach
Contracting, Manageable, and WP Zones
Strategic Boundaries
WBS Progression (Owner – Contractor)
Area /Section Based vs Discipline Based
Resource Assignment
Inter-discipline Interface
Better Accountability
Competition
Visibility
Role of Key Milestones
Risk Management & Change Management

## Slide 3
Basic WBS
- Definition
A hierarchical decomposition of the total scope to be carried out by the project team to accomplish the project objectives & create the required deliverables (by PMBook).
It visually defines the scope into manageable chunks that a project team can understand, as each level of the work breakdown structure provides further definition and details.
Level Categories (Level 0, 1, 2, 3, and so on) is not constant. It depends on the stakeholder’s perspective in reference to the project organization.
Categories may change depending on the what stage you are in the PM process. It may evolve to totally new categories. And it may grow as the work progresses through the project life cycle.
May be the driver to Contracting Strategy and Risk Management or vice versa.
Involvement of the PM is key to it’s development.
Note 1: WBS must focus on how the WORK will be better executed.
Note 2: WBS is not what will make it easy for estimating, cost allocation, OBS, RBS, etc.
Note 3: Don’t over complicate it but make it Organized and Consistent.

## Slide 4
Basic WBS
- Exercise 1

## Slide 5
Basic WBS
- WBS Progression (Owner – Contractor) (NOTE: PM Processes may overlap)
Initiating
Planning
Executing
Closing
Owner
Contractor
Level 0
Level 1
Level 2
Level 3
Level 0
Level 1
Level 4, 5 & so on
Level 3
Level 4
Level 5
Level 2
Go or No Go
Note 4: The Owner should influence through the Contract the WBS categories (Level 4 at the minimum).
Prelim Design
Bid / Sourcing
Detailed Design / Scope Build up
Commissioning
Procurement
Construction / Implementation
Closing
Executing
Initiating
Planning
Bid or No Bid
Bid Prep
Pre-Works
Construction
Commissioning
Note 5: Always determine where your Level 0 is in the overall project organization.
EBS, CBS, RBS, OBS are developed

## Slide 6
Basic WBS
- Determining Levels
Seattle
LA
Austin
NY
E&P
Construction
Commissioning
Section 1
Section 2
Section 3
Section 4
Level 0
Level 1
Level 3
Level 2
Portfolio / Program / Project Name
Constraints (geographic, time, business, systems)
EPCC
Major Section / Area
Section (Gen)
Section 3.1
Section 3.2
Section 3.3
Section 3.4
Level 4
Sub Section / Area
Civil & Mech
E&I
Hardware
Software
Level 5
Discipline / Expertise
Note 6: Each level must be consistent and on the same category. DIRECT work package related or deliverable based only.
Note 7: Avoid as much as possible to use Discipline / Expertise category before Section / Area category.
Data Centers
What happens if the certain level is not applicable?
Contracting
Manageable
WP
(Level 0)
(Level 1)
(Level 2)
(Level 3)

## Slide 7
Basic WBS
- Contracting, Manageable, and WP Zones
Contracting Level – It is the level that you may award to third parties to perform /execute. As a PM due diligence must be observed in performing proper Risks assessment as a result of the Contracting strategy.
Manageable Level – it is a level where as a PM you expect to be able to drill down in terms of reporting. It is the level where it is multi-discipline or it patterns the scope of the overall project (just a smaller version of it).
Work Package (WP) Level - it could be the deliverable. It is the level where the responsible resource is “specialized” to perform the package.
Note 8: These three classifications need especial attention and as much as possible must fall within two level range only. These zones can overlap each other.

## Slide 8
Basic WBS
- Exercise 2
projectinsight.net

## Slide 9
Basic WBS
- Exercise 2

## Slide 10
Basic WBS
- Exercise 2

## Slide 11
Basic WBS
- Exercise 3
commons.wikimedia.org

## Slide 12
Basic WBS
- Exercise 3
takomabicycle.com
commons.wikimedia.org
Build 1000 units of bicycle

## Slide 13
Basic WBS
- Exercise 3
Build 1 unit of bicycle (fully functional)
Gotham City
City of Atlantis
Metropolis City
Themyscira City

## Slide 14
Basic WBS
- Strategic Boundaries
The boundaries or demarcation line you will use to divide your project into section.
Expert judgment is the key tool to determine it.
Criteria may be geographic advantage, system based, constructability and reliability focused.
Size may not be uniform nor level of complexity.
Note 9: In creating groups make sure not to create unnecessary Interfaces.

## Slide 15
WBS Association
- Backward Approach
Construction
Area 1
Area 2
Area 3
Area 4
Sub Area 3.1
Sub Area 3.2
Sub Area 3.3
Sub Area 3.4
Sub Area 3.5
Civil & Mech
E&I
Hardware
Software
Procurement
Area 1
Area 2
Area 3
Area 4
Sub Area 3.1
Sub Area 3.2
Sub Area 3.3
Sub Area 3.4
Sub Area 3.5
Engineering
Area 1
Area 2
Area 3
Area 4
Prelim Eng.
System 1
System 2
System 3
System 4
Commissioning
System 1
System 2
System 3
System 4
Sub System 4.1
Sub System 4.2
Sub System 4.3
Sub System 4.4
Note 10: The phase(s) proceeding Construction / Implementation should adapt its WBS levels.
Design to Implement

## Slide 16
WBS Association
- Role of Key Milestones
Use Key Milestones to drive the sequence of work (high level) and include it in the contract.
Milestone criteria may include business need, operations need, constructability & reliability aspects.
Critical systems and processes on the WBS Level 1 must be included as a Key Milestone.
Note 11: Don’t assume Key Milestones are fit as a WBS category.

## Slide 17
Section vs Discipline
Construction
Section 1
Section 2
Section 3
Section 4
Civil & Mech
E&I
Hardware
Software
Construction
Civil & Mech
E&I
Hardware
Software
Section 1
Section 2
Section 3
Section 4
- Resource Assignment
PM
DPM1
DPM2
DPM3
DPM4
DL
DL
DL
DL
DL
DL
DL
DL
PE1
PE1
PE2
PE2
Note 12: You get the benefit of having to assigned mini-PM with mini sections of the project.
Section Based
Discipline Based
Note 14: This set up is only adequate if the project is relatively small.
Section 3.1
Section 3.2
Section 3.3
Section 3.4
PE1
PE2
PE1
PE3
Note 13: Depending on the size of your project, you can assign multiple mini-projects to one person.

## Slide 18
Section vs Discipline
Construction
Section 1
Section 2
Section 3
Section 4
Civil & Mech
E&I
Hardware
Software
Construction
Civil & Mech
E&I
Hardware
Software
Section 1
Section 2
Section 3
Section 4
- Inter-discipline Interface
PM
PE
PE
PE
PE
DL
DL
DL
DL
DL
DL
DL
DL
PE
PE
PE
PE
Note 15: Your mini PMs will handle the inter-discipline interface since it the part of his team.
Section Based
Discipline Based
Note 16: The set up automatically creates many Interface amongst disciplines. If issues arises, the organization may need to employ coordinators, interface engineers /managers.

## Slide 19
Section vs Discipline
Construction
Section 1
Section 2
Section 3
Section 4
Civil & Mech
E&I
Hardware
Software
Construction
Civil & Mech
E&I
Hardware
Software
Section 1
Section 2
Section 3
Section 4
- Better Accountability
PM
PE
PE
PE
PE
DL
DL
DL
DL
DL
DL
DL
DL
PE
PE
PE
PE
Note 17: The mini PMs is held liable on the package assigned to him from beginning to end. The mini PM will make sure all deliverables pre requisite to execution is provided and all issues are addressed.
Section Based
Discipline Based
Note 18: On a discipline based Level 1, the discipline lead may blame others on issues relevant to other disciplines. The discipline lead is not obligated to study the specifications, design, constraints, risks with other disciplines.
Blame
Blame
Blame

## Slide 20
Section vs Discipline
Construction
Section 1
Section 2
Section 3
Section 4
Civil & Mech
E&I
Hardware
Software
Construction
Civil & Mech
E&I
Hardware
Software
Section 1
Section 2
Section 3
Section 4
- Competition
PM
PE
PE
PE
PE
DL
DL
DL
DL
DL
DL
DL
DL
PE
PE
PE
PE
Note 19: The playing field is almost equal since then this may create an environment of healthy competition.
Section Based
Discipline Based
Note 20: The packages are distinct that it is not comparable to create competition.

## Slide 21
Section vs Discipline
Construction
Section 1
Section 2
Section 3
Section 4
Civil & Mech
E&I
Hardware
Software
Construction
Civil & Mech
E&I
Hardware
Software
Section 1
Section 2
Section 3
Section 4
- Visibility
PM
DPM1
DPM2
DPM3
DPM4
DL
DL
DL
DL
DL
DL
DL
DL
PE1
PE
PE
PE
Note 21: Progress or Issues are better analyzed when you can visualize it on where it occurs. Where the area affected can easily be isolated and apply relevant analysis.
Section Based
Discipline Based
Note 22: Though the areas or section may be visible but you have to liaise with multiple stakeholders
Section 3.1
Section 3.2
Section 3.3
Section 3.4
PE1
PE2
PE1
PE3

## Slide 22
Section vs Discipline
Construction
Section 1
Section 2
Section 3
Section 4
Civil & Mech
E&I
Hardware
Software
Construction
Civil & Mech
E&I
Hardware
Software
Section 1
Section 2
Section 3
Section 4
- Risk Management & Change Management
PM
DPM1
DPM2
DPM3
DPM4
DL
DL
DL
DL
DL
DL
DL
DL
PE1
PE
PE
PE
Note 23: Where there is visibility, few points of contact, less interface, then Risks, changes and claims are more easily managed. The Mini PM shall serve as the risks owner, change management champion for his package.
Section Based
Discipline Based
Note 24: A single risks item or change order that affects multiple section may require more people to coordinate. In terms of risks management and change management implementation the project may require additional resource as Risks Manager, change order coordinator, package champion etc.
Section 3.1
Section 3.2
Section 3.3
Section 3.4
PE1
PE2
PE1
PE3

## Slide 23
End
www.thinkhighlevel.com
<Free Download Section>
gmedalla@thinkhighlevel.com
Gholan Medalla
Website:
Email:
LinkedIn: